## Sheet1
Name of Center | Regional Transport Research and Education Centre, Kumasi (TRECK)
Institution | Kwame Nkrumah University of Science and Technology (KNUST) | [7 empty] | On Schedule
Country | Ghana | [8 empty] | Behind Schedule
Center Leader | Prof. Charles Anum Adams
Annual Workplan (Jan-Dec 2022)
Work Plan Activities | Description | 2022 Y2Q1 |  |  | 2022 Y2Q2 |  |  | 2022 Y2Q3 |  |  | 2022 Y2Q4 |  |  | Milestone/Output | Estimated Budget($) | Estimated Revenue ($) | Person Responsible
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1: Centre Management and Governance
Sub-Action 1a: Sectoral Advisory Board (SAB)
Activity 1: Sectoral Advisory Board Meeting | The Sectoral Advisory Board will have two in-person meetings at an off campus hotel facility. The SAB comprises of both regional and national members, thus the amount quoted will include cost of flights, accommodation and other related expenses hence the need for the budgeted amount. | [12 empty] | Minutes of SAB meetings | 40000 |  | Centre Director & SAB Secretary | bar: 2022 Y2Q1 Feb; 2022 Y2Q2 Apr; 2022 Y2Q2 Jun; 2022 Y2Q3 Sep; 2022 Y2Q4 Dec
Sub-Action 1b: Internation Scientific Advisory Board (ISAB)
Activity 1: International Scientific Advisory Board Meeting | The Leadership of the Centre will present the programmes and research status to the ISAB for feedback prior to their virtual meeting. At least one in-person visit is planned for the Chair to give a seminar | [12 empty] | Minutes of ISAB meetings | 5000 |  | Centre Director & SAB Secretary | bar: 2022 Y2Q1 Mar; 2022 Y2Q3 Jul; 2022 Y2Q4 Nov
Sub-Action 1C: Meetings
Activity 1: Meetings of Centre Leadership | Monthly Centre Leadership meetings for deliberations on the project. Weekly Core operational staff meetings will be held | [12 empty] | Minutes of Management meetings | 8000 |  | Centre Director, Project Manager
Activity 2: Country Steering Committee meetings | Participation in twice per year country steering committee meetings | [13 empty] | 2000 |  | Centre Director, Project Manager | bar: 2022 Y2Q1 Mar; 2022 Y2Q4 Nov
Action 2: DLI 3 Action: Quantity of Students
Sub-Action 2a: Recruitment of Students
Activity 1: Recruitment of Students | Online advertisement, brochures, fliers, exhibit Centre presence at international and regional conferences | [12 empty] | Ten (10) PhD and twenty (20) Masters students recruited | 2000 | 150000 | Academic coordinator and Project Manager | bar: 2022 Y2Q1 Jan to 2022 Y2Q3 Aug
Activity 2: Training of existing and potential students in MSc and PhD programmes | Blended learning activities, seminars, workshops and conferences. Payment of fees, stipend and accomodation for some students | [12 empty] | Graduation of Masters students | 405000 |  | Deputy centre Director, Academic coordinator and Project Manager
Sub-Action 2b: Short courses
Activity 1: Local Short Courses | In-person short courses to address local industry +national needs | [12 empty] | Hundred (100) national short course participants | 5000 |  | Centre Director, Industry Liaison officer | bar: 2022 Y2Q1 Jan to 2022 Y2Q1 Feb; 2022 Y2Q3 Sep
Sub-Action 2c: Faculty and staff training and development
Activity 1: In-house training for staff | Training for blended learning facilitation | [12 empty] | Motivated staff with blended learning facilitation skills | 10000 |  | Deputy Centre Director | bar: 2022 Y2Q1 Jan; 2022 Y2Q3 Jul
Activity 2: Continuous professional development | Centre staff and faculty participation in external short courses | [12 empty] | Staff with the requisite skill set for Centre activities | 40000 | 100000 | Deputy Centre Director
Action 3:DLI 4:Quality of Education
Sub-Action 3a: Gap Assessment
Activity 1: Conclusion of Gap Assessment | As part of the process for national and international accreditation of programmes, we will finsih with the gap assessment | [12 empty] | Consultant's report containing gaps and recommendations | 15000 | 100000 | Centre Director, Academic Cordinator and Deputy Centre Leader | bar: 2022 Y2Q1 Jan to 2022 Y2Q1 Feb
Sub-Action 3b: Accreditation
Activity 1: New Programme Accreditation | Complete outstanding activities and meet the requirement of the National Accreditation Board for the MSc Transport Leadership programme | [12 empty] | New academic programme accredited and running | 10000 | 100000 | Deputy Centre Director, Project Manager
Activity 2: International Accreditation | Begin activities to acquire international accreditation for TRECK programmes | [12 empty] | Begin engagement with AQAS for international certification | 70000 | 100000 | Centre Director, Deputy Centre Leader and Academic Cordinator | bar: 2022 Y2Q1 Mar to 2022 Y2Q4 Dec
Sub-Action 3c: Infrastructure Improvement
Activity 1a: TRECK Office Complex | Complete procurement processes | [12 empty] | Contractor engaged | bar: 2022 Y2Q1 Jan to 2022 Y2Q1 Mar
Activity 1b: TRECK Office Complex | Begin civil works | [12 empty] | Civil works commenced | 400000 | 300000 | Centre Director, Procurement Officer, Finance Manager | bar: 2022 Y2Q2 Apr to 2022 Y2Q4 Dec
Activity 2: Procurement of teaching equipment and lab consumables | Procure equipment to facilitate online learning and teaching and also lab consumables | [12 empty] | Well equipped teaching and research lab established, learning management system and lab consumables procured | 200000 |  | Centre Director, Procurement Officer, Finance Manager | bar: 2022 Y2Q1 Jan to 2022 Y2Q2 Jun
Action 4: DLI 5: Relevance of Research
Sub-Action 4a: Internship
Activity 1: Students and Faculty members on internships | Sourcing for companies for students and faculty members placements. Also actual intenships to be undertaken and allowances paid. | [12 empty] | 50 Faculty members and students embark on intenship | 50000 | 50000 | Industrial Liaison Officer and Project Manager | bar: 2022 Y2Q3 Aug to 2022 Y2Q4 Dec
Sub-Action 4b: Regional Conference
Activity 1: Conference on sustainable Transport & Logistics | Plan and implement a Regional Conference on Transport and Logistics with national and regional partners. | [12 empty] | Regional conference for Sustainable Transport & logistics report | 10000 |  | Centre Director, Project Manager | bar: 2022 Y2Q2 May; 2022 Y2Q3 Aug
Sub-Action 4c: Industry and Academic applied research
Activity 1: Undertake research with industries and academia | Centre will liaise with industry and academic partners in the region to undertake research to address industry and developmental needs | [12 empty] | Research report indicating workshop with stakeholders for research prospecting and implementation. The amount will be leveraged as TRECK seed capital for industry to match. | 30000 |  | Deputy Centre Director, Academic Cordinator and Industry Liaison Officer
Sub-Action 4d: Externally Generated Funds
Activity 1: Develop ACE student/faculty innovation and entrepreneurship activities | Organize entreprenuership events for students/faculty | [12 empty] | Students equiped and motivated to start their business | 50000 |  | Industrial Liaison Officer and Project Manager
Sub-Action 4e: Center Visibility
Activity 1a: Center Visibility | Undertake various activities to make the Centre visible in the region | [13 empty] | 10000 |  | Communications Officer
Activity 1b: Web presence | Maintain the Centre's website and update with Centre's activities and revelant documents | [12 empty] | A well maintained website with the necessary information and Centre documents | 2000 |  | Finance Manager
Activity 2: Centre's presence at Workshops and Conferences | Staff and PhD students attendance at national, regional and international conferences on Transport to present papers, keynote speakers etc, Publish newsletter, research and policy briefs and exhibits at workshops and conferences. | [12 empty] | Report on Conferences, Presentations and publication, exhibitions and Workshops | 20000 |  | Centre Director | bar: 2022 Y2Q3 Jul to 2022 Y2Q3 Sep
Activity 3: Engagement with Industry | TRECK leadership to engage Industry to identify possible areas for cooperation | [13 empty] | 10000 |  | Centre Director
Action 5: DLI 6: Timeliness and quality of fiduciary management
Sub-Action 4a: Timely Fiduciary Reporting
Activity 1a: Audit of the Centre's financial transactions by Internal Auditors | Financial and Procurement Audit of the Centre's transactions and procurement activities | [12 empty] | Internal Audit report for the year 2021 | 10000 | 50000 | Finance Manager | bar: 2022 Y2Q1 Feb
Activity 1b: Financial and Procurement Audit undertaken by External Auditors | Financial and Procurement Audit of the Centre's transactions and procurement activities | [12 empty] | Financial and Procurement Audit report for the year 2021 |  |  | Finance Manager | bar: 2022 Y2Q1 Mar
Activity 2: Preparation of IFR for the period ending June 30th and Dec, 31st | Preparation of IFR and submission to the World Bank and also uploading on the Centre's website | [12 empty] | IFR prepared and sumitted to the World Bank |  |  | Finance Manager | bar: 2022 Y2Q3 Aug; 2022 Y2Q4 Dec
Sub-Action 4b: Functional Institutional Oversight of Fiduciary Mgt
Activity 1: Submite audited Financial Statements for review by the University's Audit Committee | Minutes from the University's Audit Committee meeting | [12 empty] | Submission of a letter containing the names of the Internal Audit Committee of KNUST |  |  | Finance Manager | bar: 2022 Y2Q3 Jul
Sub-Action 4c: Web Transparency of ACE Expenditures
Activity 1: Annual work plan will be prepared and approved, budget, IFR and Procurement Audit reports completed | Annual work plan, budget, IFR and Financial and Procurement Audit reports uploaded to website | [12 empty] | Annual work plan will be prepared and approved, budget, IFR and Procurement Audit reports uploaded to website |  |  | Finance Manager | bar: 2022 Y2Q1 Feb; 2022 Y2Q3 Jul
Sub-Action 4d: Quality of Procurement Planning
Activity 1: Procurement Planning | Annual procurement plan will be shared with AAU and uploaded to website | [12 empty] | Original approved procurement plan and annual procurement plan will be shared with AAU and uploaded to website |  |  | Finance Manager | bar: 2022 Y2Q1 Jan
| TOTAL | [13 empty] | 1404000 | 950000
| The Centre is projecting a Cash balance of $1,700,000.00 at the end of 2021. Part will be used to finance the deficit of $454,000.00 in 2022. | [13 empty] | 454000
Note on B27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Center or institution?
Note on B47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (Shouldn't it be merged with above Activity 1 of Sub Action 4b: ...Conference? )

## Sheet2
| Num | rate | amt
| 100 | 400 | 40000
| 50 | 800 | 40000
| 25 | 750 | 18750
| 15 | 450 | 6750
10000
35500
ISAB Hotel | 5 | 150 | 750
Allowance | 5 | 200 | 1000
Air fare |  |  | 2000
3750